# FREDDYMANUEL.COM

Portfolio Website & NFT Launch Roadmap

Master Checklist & Action Plan

Document Version: 1.0

December 2025

# PROJECT OVERVIEW

This document outlines a two-phase approach to launching your professional portfolio and entering the NFT art market. Phase 1 focuses on establishing your online presence with freddymanuel.com, while Phase 2 prepares and launches your Cosmopolitical City series as NFTs on curated platforms.

## Project Goals

- Launch professional portfolio website on freddymanuel.com

- Showcase artistic research (Internercia, Park, Cosmopolitical City, Nepal, True Tales, Coro Interno)

- Display technical projects (Olympian Power Cleaners, AI chatbot, Diaries of the Upheaval)

- Establish NFT presence on curated platforms (Foundation or SuperRare)

- Mint 3-5 pieces from Cosmopolitical City series as genesis collection

## Timeline Overview

Phase 1: Weeks 1-3

Website design, development, and launch

Phase 2: Months 2-3

NFT platform application, wallet setup, artwork preparation, minting

# PHASE 1: WEBSITE LAUNCH

Priority: IMMEDIATE | Timeline: 2-3 weeks

## Week 1: Planning & Decision

### Platform Decision

- Check if Canva supports custom domain (freddymanuel.com)

- Review Canva's limitations (branding, load speed, customization)

- Decide: Stay on Canva OR migrate to Cloudflare Pages

- If Cloudflare: Review technical requirements and timeline

### Content Audit

- Review all existing Canva pages (Homepage, ONGoing, ARTWORK, UI/UX + AI)

- Verify all text is final and accurate

- Check that all project descriptions are complete

- Ensure contact information (LinkedIn, GitHub, Email) is up to date

### Asset Preparation

- Organize images in Google Drive folders by project

- Verify high-res scans of Cosmopolitical City series (9922 x 6652 px)

- Collect Internercia, Park, Nepal, YUM, Coro Interno images

- Prepare Olympian Power Cleaners screenshots

- Gather Diaries of the Upheaval project visuals

## Week 2-3: Development & Launch

### If Staying on Canva

- Complete any missing sections (About, Services, Contact if needed)

- Add placeholder 'NFT Gallery - Coming Soon' section

- Connect freddymanuel.com domain in Canva settings

- Test site on desktop and mobile devices

- Publish and verify domain is live

### If Migrating to Cloudflare

- Set up Cloudflare account (already exists: Account ID fe9931c9...)

- Create GitHub repository for website code

- Build HTML/CSS/JS version matching Canva aesthetic

- Set up Cloudflare R2 bucket for image hosting

- Upload and optimize all images to R2

- Deploy to Cloudflare Pages via GitHub integration

- Connect freddymanuel.com domain to Cloudflare Pages

- Set up contact form with Cloudflare Workers + D1 database

- Test site thoroughly on all devices and browsers

- Launch and announce on LinkedIn/social media

### Post-Launch

- Update LinkedIn profile with website link

- Add website to GitHub profile bio

- Share portfolio on relevant communities (Behance, Dribbble)

- Monitor analytics and fix any issues

# PHASE 2: NFT GALLERY SETUP

Priority: SECONDARY | Timeline: 1-2 months after website launch

## Month 1: Education & Platform Selection

### Crypto Basics

- Learn about blockchain fundamentals (Ethereum, Polygon, Tezos)

- Understand NFT ownership vs copyright

- Research gas fees and blockchain costs

- Study successful NFT artists and pricing strategies

### Wallet Setup

- Install MetaMask browser extension

- Create new wallet and secure seed phrase (NEVER share this!)

- Add Ethereum mainnet and test networks

- Practice sending/receiving small amounts on testnet

- Purchase small amount of ETH for gas fees

### Platform Research & Application

- Research Foundation (foundation.app) - curated, 1/1 art focus

- Research SuperRare (superrare.com) - ultra-curated, prestigious

- Research KnownOrigin (knownorigin.io) - curated, easier entry

- Research Objkt (objkt.com) - Tezos, low fees, photography-friendly

- Choose primary platform (Recommendation: Foundation)

- Prepare application portfolio (CV, exhibition history, artist statement)

- Submit application with freddymanuel.com link

- Wait for approval (can take 1-4 weeks)

## Month 2: Artwork Preparation & Metadata

### Artwork Selection

- Review Cosmopolitical City inventory spreadsheet

- Select 3-5 pieces for genesis collection (mix of towers, splashes, explosions)

- Verify ownership status of selected pieces

- Decide: NFT only OR NFT + physical piece

### Image Optimization

- Export high-res versions (9922 x 6652 px maintained)

- Convert to PNG or JPEG (PNG recommended for archival)

- Optimize file sizes (aim for 5-10MB per image)

- Add color profiles (sRGB standard for web)

- Create thumbnail versions (1200 x 800 px for previews)

### IPFS Upload

- Create account on NFT.Storage (free IPFS hosting)

- Upload images to IPFS via NFT.Storage

- Save IPFS CIDs (Content Identifiers) for each image

- Verify images are accessible via Cloudflare IPFS gateway

### Metadata Creation

- Write detailed description for each piece (include process, materials, context)

- Create JSON metadata files with attributes (year, medium, series, exhibition)

- Add external_url field pointing to freddymanuel.com

- Write artist statement about the series and NFT project

### Pricing Strategy

- Research comparable artists' pricing on chosen platform

- Consider: Your €350-€1,500 physical prices = 0.3-0.5 ETH NFT range

- Set primary sale price for each piece

- Determine royalty percentage for secondary sales (10% standard)

## Month 2-3: Minting & Launch

### Minting Process

- Connect MetaMask wallet to chosen platform

- Create collection 'Cosmopolitical City' with description

- Upload artwork #1 with metadata

- Review and confirm all details before minting

- Pay gas fee and mint NFT (wait for blockchain confirmation)

- Repeat for remaining 2-4 pieces

- List NFTs for sale at predetermined prices

### Website Integration

- Update freddymanuel.com NFT section from 'Coming Soon' to live gallery

- Embed collection from Foundation/SuperRare

- Add links to individual NFT listings

- Write explanation of what NFTs are and why you're using them

- Add your wallet address for collectors to view provenance

### Marketing & Promotion

- Announce NFT launch on LinkedIn with backstory

- Share on Twitter/X with hashtags: #NFTart #CryptoArt #TezosArt

- Post process documentation: toner discovery → kitchen oven → NFT

- Engage with crypto art communities on Discord/Twitter

- Share Festival Latina Middle East 2016 exhibition history

- Create 1-2 min video explaining toner alchemy process

- Consider submitting to NFT art blogs/publications

# NFT PLATFORM COMPARISON

| Platform | Prestige | Fees | Best For |
| --- | --- | --- | --- |
| Foundation | HIGH | 15% | Curated 1/1 art, strong collector base |
| SuperRare | VERY HIGH | 15% | Ultra-curated, museum-quality, hardest to get into |
| KnownOrigin | MEDIUM | 15% | Curated but easier entry, digital art focus |
| Objkt (Tezos) | MEDIUM | 2.5% | Low fees, eco-friendly, photography/fine art |

Recommendation: Foundation

Foundation offers the best balance of prestige, collector base, and accessibility for your first NFT drop. Your exhibition history (Festival Latina Middle East 2016) and BFA credentials make you a strong applicant.

# PRICING STRATEGY

## Physical Artwork Prices (Current)

Based on your Cosmopolitical City inventory spreadsheet:

• Small pieces (23 x 30 cm): €350

• Medium pieces (42 x 28 cm): €650

• Diptychs: €800-€1,500

• Special pieces (collages, portraits): €750-€1,000

## NFT Pricing Recommendation

Genesis Collection (First 3-5 Pieces):

0.3 - 0.5 ETH per piece (~€750-€1,250 at current rates)

Rationale:

• Aligns with your physical artwork pricing

• Positions you as emerging but serious artist

• Exhibition history justifies premium over untested artists

• BFA + Festival Latina Middle East 2016 adds credibility

• Unique process (toner alchemy) creates narrative value

## Secondary Sales Royalty

Set at 10% (industry standard) - You receive 10% of any future resales automatically via smart contract

## Rights & Licensing

What NFT buyer gets:

• Ownership of digital artwork file

• Right to display publicly (online, in exhibitions)

• Right to resell (with 10% going to you)

• Provenance verification via blockchain

What you retain:

• Copyright and reproduction rights

• Commercial use rights

• Right to create additional works in the series

# TECHNICAL SETUP GUIDE

## Cloudflare Infrastructure (Website)

Account Details:

Account ID: fe9931c9a72313dcdccba4be02e08d04

Domain: freddymanuel.com (already purchased)

Services to Use:

• Cloudflare Pages: Static site hosting (FREE unlimited bandwidth)

• R2 Storage: Image hosting (~$0.015/GB/month for ~1GB = $0.015)

• Workers: Contact form backend (100k requests/day FREE)

• D1 Database: Contact form storage (FREE tier: 100k reads/day)

• IPFS Gateway: NFT artwork hosting (FREE)

Estimated Monthly Cost: ~$0.03 (essentially free)

## MetaMask Wallet Setup

Step-by-Step:

- Install MetaMask extension for Chrome/Firefox/Brave

- Click 'Create a Wallet' and set password

- CRITICAL: Write down 12-word seed phrase on PAPER (never digital)

- Store seed phrase in secure location (safe, bank deposit box)

- Verify seed phrase by entering words in correct order

- Add Ethereum mainnet (should be default)

- Optional: Add testnet (Sepolia) for practice

- Your wallet address starts with '0x...' - this is public, shareable

⚠️ SECURITY WARNING

• NEVER share your seed phrase with anyone (not even Anthropic support, MetaMask, or exchanges)

• NEVER enter seed phrase on websites (only in MetaMask during initial setup)

• NEVER screenshot or digitally store your seed phrase

• If you lose seed phrase, you lose access to wallet FOREVER

# MARKETING & PROMOTION PLAN

## Portfolio Launch Announcement

LinkedIn Post Template:

"Excited to share my new portfolio website: freddymanuel.com
As an artist and AI engineer, I explore the intersection of physical materiality and digital systems. My work spans installation art, video performance, and machine learning - from baking printer toner in domestic ovens to building conversational AI agents.
The site features projects like Cosmopolitical City (exhibited at Festival Latina Middle East 2016), my ongoing Coro Interno installation exploring ADHD and anxiety through multi-agent AI, and technical work including full-stack web development.
Check it out and let me know what you think!"

## NFT Launch Announcement

Multi-Platform Strategy:

LinkedIn: Professional audience, exhibition history, process documentation

Twitter/X: Crypto art community, use hashtags #NFTart #CryptoArt #CleanNFT

Instagram: Visual showcase, process videos, behind-the-scenes

Discord: Join NFT art communities, engage authentically

## Story Angles

Your unique narrative:

• From trash to treasure: Finding toner cartridges at Dragon Mart

• Kitchen alchemy: Using domestic oven to create fine art

• Dubai's synthetic landscape: Exploring hypermodern urbanism through materials

• Artist to AI engineer: Natural progression exploring digital materiality

• Physical-to-digital transformation: From gallery walls to blockchain

## Content Calendar (First Month)

Week 1: Genesis drop announcement

• Announce collection with hero image

• Share artist statement about why NFTs

Week 2: Process documentation

• Video showing toner + heat transformation

• Time-lapse of creation process

Week 3: Exhibition history

• Share Festival Latina Middle East 2016 photos

• Curator testimonial (Mariana Turcho)

Week 4: Collector engagement

• Q&A about the series

• Highlight individual pieces with detail shots

# RESOURCES & LINKS

## Key Assets

• Canva Portfolio: freddymanuel.my.canva.site/portfolio

• Google Drive - Main Folder: drive.google.com/drive/.../1_xaic3NfjvTSpZXQ33_uz4jfuF6o3O05

• CANVAS Folder (edited images): drive.google.com/.../1LCK_KcOKD5dUZo5O85hGhalFA3qu3_f5

• Cosmopolitical City high-res: drive.google.com/.../1RZ01SVdcwwX2MM4Hb__kgQRbVgNPY7uK

• Inventory Spreadsheet: docs.google.com/spreadsheets/.../1O7oZcUMATaxTdiwh0EB1XLrKAJIO5B-wX-3J00YpHv4

## NFT Platforms

• Foundation: foundation.app

• SuperRare: superrare.com

• KnownOrigin: knownorigin.io

• Objkt: objkt.com

## Technical Tools

• Cloudflare Dashboard: dash.cloudflare.com

• MetaMask: metamask.io

• NFT.Storage (free IPFS): nft.storage

• GitHub: github.com (for website hosting)

END OF CHECKLIST

Good luck with your launch! 🚀